## Sheet1
SPRINT 1 ( SEP 12 - SEP 25)
Bi-Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Vamshidhar Reddy Parupally | Decide on wireframes and ways to track the progress, scrum board and set up repo | Design the routing flow for the users, Landing/Homepage for the user | None
Manish Kovelamudi | Deciding on what should be the Architecture of the Project | Design and develope Airline Employee Dashboard | None
Anurag Gajam | Deciding on backend Technology and design | Design Rest APIs | None
Ananya Mandava | Sprint Details and Task allocation | Design and develop Flight status page | None
Scrum Master = Vamshidhar Reddy Parupally
XP Core Value
1. Courage | We needed courage to take up the task and implement all out task on time.
2. Comunication | We followed Communication during this Weekly Scrum since it is necessary to update everybody about our work
3. Simplicity | It is necessary to keep our code simple so that others can tak over incase one is not present
SPRINT 2 ( SEP 26 - OCT 9)
Bi-Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Vamshidhar Reddy Parupally | Design the routing flow for the users, Landing/Homepage for the user | Add airport employee page for changing the baggage gates, search and filter and time based scheduling | None
Manish Kovelamudi | Design and develope Airline Employee Dashboard | Add airline employee pages | None
Anurag Gajam | Design Rest APIs | API creation for airport employee functions | None
Ananya Mandava | Design and develop Flight status page | Add flight status pages | None
Scrum Master = Vamshidhar Reddy Parupally
XP Core Value
1. Feedback | We took feedback for our work and also provided what we felt about others work.
2. Comunication | We followed Communication during this Scrum since it is necessary to keep every team member upto date about the work
3. Simplicity | It is necessary to keep our code simple so that others can tak over incase one is not present
SPRINT 3 ( OCT 10 - OCT 23)
SPRINT 3 ( OCT 10 - OCT 23)
Bi-Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Vamshidhar Reddy Parupally | Add airport employee page for changing the baggage gates, search and filter and time based scheduling | Airport Employee tasks (gate management) | None
Manish Kovelamudi | Add airline employee pages | Airline Api to fetch data | None
Anurag Gajam | API creation for airport employee functions | dynamic gate assignment for flight, api to retirve flights schedule | None
Ananya Mandava | Add flight status pages | to work on flight schedule component | None
Scrum Master = Vamshidhar Reddy Parupally
XP Core Value
1. Feedback | We took feedback for our work and also provided what we felt about others work.
2. Comunication | We followed Communication during this Scrum since it is necessary to keep every team member upto date about the work
3. Simplicity | It is necessary to keep our code simple so that others can tak over incase one is not present
SPRINT 4 ( OCT 24 - NOV 06)
Bi-Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Vamshidhar Reddy Parupally | Airport Employee tasks (gate management) | Handle erorrs in the application | None
Manish Kovelamudi | Airline Api to fetch data | Airline employee update and adding new flights and api for the same | None
Anurag Gajam | dynamic gate assignment for flight, api to retirve flights schedule | fixes to gate contoller, login controller components | None
Ananya Mandava | Flight schedule component | home page and schedule flight pages components | None
Scrum Master = Vamshidhar Reddy Parupally
XP Core Value
1. Feedback | We took feedback for our work and also provided what we felt about others work.
2. Comunication | We followed Communication during this Scrum since it is necessary to keep every team member upto date about the work
3. Courage | Courage to ask for more time and keep the work on time
4. Simplicity | It is necessary to keep our code simple so that others can tak over incase one is not present
SPRINT 5 ( NOV 07 - NOV 25)
Bi-Weekly Scrum Report
Team Member | Completed Task | Upcoming Task | Tasks Blocked
Vamshidhar Reddy Parupally | Error handling for login and redirection for search | None | None
Manish Kovelamudi | Airline employee update and adding new flights and api for the same | NONE | None
Anurag Gajam | fixes to gate contoller, login controller components | NONE | None
Ananya Mandava | home page and schedule flight pages components | NONE | None
Scrum Master = Vamshidhar Reddy Parupally
XP Core Value
1. Feedback | We took feedback for our work and also provided what we felt about others work.
2. Comunication | We followed Communication during this Scrum since it is necessary to keep every team member upto date about the work